## README
Oracle Fusion Pod — Implementation Dependency & RACI Tracker
Companion tracker to the agentic onboarding guide. Drives Provision -> Install -> Foundation -> Modules.
How to use this workbook
1. Phase 0 – Install | Tick off post-provisioning install & access steps before any functional setup.
2. Discovery | Capture the design decisions (COA, ledger, LE/BU, security, data) with the client. These anchor everything.
3. Module Tracker | The master list: 46 tasks across phases. Set Status + RACI owners + dates. Status drives the dashboard.
4. Dependencies | Every prerequisite edge, so you can see what blocks what. 'Blocked?' flags tasks whose prereqs aren't Done.
5. SQL Validation | Detect & validate (PASS/FAIL) BIP SQL per object; run before opening downstream modules.
6. Dashboard | Live roll-up by pillar and phase from the Module Tracker.
RACI legend | R=Responsible (does the work) A=Accountable (owns outcome) C=Consulted I=Informed
Status values | Not Started / In Progress / Done / N/A / Blocked
Golden rule | Foundation (Phase 1) must be Done and validated before Phase 2+ modules begin. Re-keying it later = re-implementation.

## 1. Phase 0 - Install
Phase 0 — Post-Provisioning Install & Access
# | Step | What it covers | Done?
1 | Receive pod details & service admin access | Capture test & prod pod URLs, identity domain, and the initial service administrator credentials from the activation email. | No
2 | Configure identity (IAM/IDCS) & SSO | Set up the identity domain, federation/SSO with the client IdP, password policy, and MFA. Provision the first implementation users. | No
3 | Security Console baseline | Copy seeded roles to custom roles, set role hierarchy strategy, and define the data-security approach before provisioning functional users. | No
4 | Outbound email & notifications | Configure email server / from-address, BI delivery, and approval notifications so workflows and reports can send. | No
5 | Environment strategy (Test ↔ Prod, P2T) | Confirm number of environments, refresh (P2T) cadence, and how config moves (configuration packages / migration sets) test→prod. | No
6 | Enable offerings in Functional Setup Manager | Turn on the offerings for in-scope pillars (Financials, Procurement, SCM, HCM, CX, etc.). This is the master switch that reveals setup tasks. | No
7 | Create implementation project & setup strategy | Decide UI task-list vs export/import setup, define the implementation project, and assign setup task owners. | No
8 | Sandbox & extensibility strategy | Establish sandbox naming/governance for page/object extensions and the publish workflow. | No
9 | Release readiness process | Set the process for quarterly Fusion updates: read what's new, regression test in test pod, then apply to prod. | No

## 2. Discovery
Discovery — Design Decisions (capture with client BEFORE config)
Area | Question | Client Answer / Decision | Decided By
Program | Which pillars are go-live wave 1 vs later?
Program | Target go-live date(s) and hard fiscal/regulatory deadlines?
Program | Legacy systems replaced and their data quality?
Program | Key integrations (bank, tax engine, CPQ, Eloqua, payroll)?
Foundation (Common) · Chart of Accounts (segments & value sets) | How many segments and what (Company, Cost Center, Account, Product, Intercompany, Future)?
Foundation (Common) · Chart of Accounts (segments & value sets) | Segment lengths & value set sizes?
Foundation (Common) · Chart of Accounts (segments & value sets) | Hierarchies/trees needed for reporting?
Foundation (Common) · Chart of Accounts (segments & value sets) | Natural account = account segment qualifier?
Foundation (Common) · Primary Ledger (+ SLA method) | One ledger or many (multi-country)?
Foundation (Common) · Primary Ledger (+ SLA method) | Accounting method (Standard Accrual)?
Foundation (Common) · Primary Ledger (+ SLA method) | Secondary ledger / reporting currency needed?
Foundation (Common) · Primary Ledger (+ SLA method) | Ledger set / balancing rules?
Foundation (Common) · Legal Entities & jurisdictions | How many legal entities / countries?
Foundation (Common) · Legal Entities & jurisdictions | Registration numbers & jurisdictions?
Foundation (Common) · Legal Entities & jurisdictions | Which LE is the ledger's default?
Foundation (Common) · Business Units & functions | How many BUs and on what basis (geo, line of business, shared services)?
Foundation (Common) · Business Units & functions | Which functions per BU (Payables, Receivables, Procurement, OM, Billing)?
Foundation (Common) · Business Units & functions | Shared service center model?
Foundation (Common) · Reference Data Sets (SetID) | Common set for all, or partitioned reference data?
Foundation (Common) · Reference Data Sets (SetID) | Which set-enabled objects need partitioning?
Foundation (Common) · Security: roles, data roles, users | SSO/IDCS federation or local accounts?
Foundation (Common) · Security: roles, data roles, users | Role mapping per persona?
Foundation (Common) · Security: roles, data roles, users | Data scoping by BU/LE/business unit security?
Foundation (Common) · Security: roles, data roles, users | SoD policy / audit requirements?
Customer Data Cleansing · Customer Data Cleansing & TCA load | Source systems & record counts?
Customer Data Cleansing · Customer Data Cleansing & TCA load | Dedup/match rules & survivorship?
Customer Data Cleansing · Customer Data Cleansing & TCA load | Account vs party hierarchy needed?
Customer Data Cleansing · Customer Data Cleansing & TCA load | Address validation source?
Customer Data Cleansing · Customer Data Cleansing & TCA load | Sales account vs customer (AR) account split understood?
Customer Data Cleansing · Customer master (Accounts & Sites) | Bill-to/ship-to site model?
Customer Data Cleansing · Customer master (Accounts & Sites) | Account hierarchy/parenting?
Customer Data Cleansing · Customer master (Accounts & Sites) | Payment terms per account/site?
Customer Data Cleansing · Customer master (Accounts & Sites) | Sales account assignment for CX?
SCM / Procurement / Mfg · Inventory orgs & Item Master (PIM) | Inventory org structure (master + child)?
SCM / Procurement / Mfg · Inventory orgs & Item Master (PIM) | Item classes & attributes?
SCM / Procurement / Mfg · Inventory orgs & Item Master (PIM) | Catalogs & categories?
SCM / Procurement / Mfg · Inventory orgs & Item Master (PIM) | Conversion source for items?
HCM · Workforce structures (Legal Employer, Depts, Jobs, Grades) | Job vs position management?
HCM · Workforce structures (Legal Employer, Depts, Jobs, Grades) | Department tree?
HCM · Workforce structures (Legal Employer, Depts, Jobs, Grades) | Grades & grade ladders?
HCM · Workforce structures (Legal Employer, Depts, Jobs, Grades) | Legal employers per country?

## 3. Module Tracker
Module Tracker — Status, RACI & Dependencies
ID | Phase | Pillar | Task | Prerequisites | Status | Blocked? | Responsible (R) | Accountable (A) | Consulted (C) | Informed (I) | Target Date | Notes
geo | 1 | Foundation (Common) | Geographies (TCA) | — | Not Started | Ready
ent | 1 | Foundation (Common) | Enterprise definition | Geographies (TCA) | Not Started | BLOCKED
cur | 1 | Foundation (Common) | Currencies & conversion rates | Enterprise definition | Not Started | BLOCKED
coa | 1 | Foundation (Common) | Chart of Accounts (segments & value sets) | Currencies & conversion rates | Not Started | BLOCKED
cal | 1 | Foundation (Common) | Accounting calendar | Currencies & conversion rates | Not Started | BLOCKED
led | 1 | Foundation (Common) | Primary Ledger (+ SLA method) | Chart of Accounts (segments & value sets), Accounting calendar | Not Started | BLOCKED
le | 1 | Foundation (Common) | Legal Entities & jurisdictions | Primary Ledger (+ SLA method) | Not Started | BLOCKED
bu | 1 | Foundation (Common) | Business Units & functions | Legal Entities & jurisdictions | Not Started | BLOCKED
setid | 1 | Foundation (Common) | Reference Data Sets (SetID) | Business Units & functions | Not Started | BLOCKED
loc | 1 | Foundation (Common) | Locations | Enterprise definition, Geographies (TCA) | Not Started | BLOCKED
sec | 1 | Foundation (Common) | Security: roles, data roles, users | Enterprise definition | Not Started | BLOCKED
data_clean | 2 | Customer Data Cleansing | Customer Data Cleansing & TCA load | Geographies (TCA) | Not Started | BLOCKED
cust | 2 | Customer Data Cleansing | Customer master (Accounts & Sites) | Customer Data Cleansing & TCA load, Business Units & functions | Not Started | BLOCKED
fin_gl | 2 | ERP / Financials | General Ledger | Primary Ledger (+ SLA method), Security: roles, data roles, users | Not Started | BLOCKED
fin_tax | 2 | ERP / Financials | Tax | Legal Entities & jurisdictions, Geographies (TCA) | Not Started | BLOCKED
scm_sup | 2 | SCM / Procurement / Mfg | Supplier model | Business Units & functions, Security: roles, data roles, users | Not Started | BLOCKED
scm_inv | 2 | SCM / Procurement / Mfg | Inventory orgs & Item Master (PIM) | Business Units & functions, Legal Entities & jurisdictions | Not Started | BLOCKED
hcm_ws | 2 | HCM | Workforce structures (Legal Employer, Depts, Jobs, Grades) | Business Units & functions, Locations | Not Started | BLOCKED
fin_cm | 3 | ERP / Financials | Cash Management & Banks | General Ledger | Not Started | BLOCKED
fin_ap | 3 | ERP / Financials | Payables (AP) | General Ledger, Tax, Supplier model, Cash Management & Banks | Not Started | BLOCKED
fin_ar | 3 | ERP / Financials | Receivables (AR) | General Ledger, Tax, Customer master (Accounts & Sites) | Not Started | BLOCKED
fin_fa | 3 | ERP / Financials | Fixed Assets (FA) | General Ledger | Not Started | BLOCKED
scm_price | 3 | SCM / Procurement / Mfg | Pricing | Inventory orgs & Item Master (PIM) | Not Started | BLOCKED
scm_proc | 3 | SCM / Procurement / Mfg | Purchasing & Self-Service Procurement | Supplier model, Inventory orgs & Item Master (PIM) | Not Started | BLOCKED
hcm_core | 3 | HCM | Core HR (workers & assignments) | Workforce structures (Legal Employer, Depts, Jobs, Grades), Security: roles, data roles, users | Not Started | BLOCKED
cx_res | 3 | CX (Sales/Service/CPQ) | CX Sales: Resources & Sales hierarchy | Security: roles, data roles, users, Customer master (Accounts & Sites) | Not Started | BLOCKED
cx_prod | 3 | CX (Sales/Service/CPQ) | CX Sales: Products & Catalog | Inventory orgs & Item Master (PIM) | Not Started | BLOCKED
fin_exp | 4 | ERP / Financials | Expenses | Payables (AP), Core HR (workers & assignments) | Not Started | BLOCKED
scm_om | 4 | SCM / Procurement / Mfg | Order Management + Global Order Promising | Inventory orgs & Item Master (PIM), Pricing, Customer master (Accounts & Sites), Receivables (AR) | Not Started | BLOCKED
scm_cost | 4 | SCM / Procurement / Mfg | Cost Management | Inventory orgs & Item Master (PIM), General Ledger | Not Started | BLOCKED
scm_mfg | 4 | SCM / Procurement / Mfg | Manufacturing | Inventory orgs & Item Master (PIM) | Not Started | BLOCKED
hcm_abs | 4 | HCM | Absence Management | Core HR (workers & assignments) | Not Started | BLOCKED
hcm_pay | 4 | HCM | Payroll | Core HR (workers & assignments) | Not Started | BLOCKED
hcm_cmp | 4 | HCM | Compensation & Benefits | Core HR (workers & assignments) | Not Started | BLOCKED
cx_terr | 4 | CX (Sales/Service/CPQ) | CX Sales: Territories | CX Sales: Resources & Sales hierarchy, Customer master (Accounts & Sites) | Not Started | BLOCKED
cx_sales | 4 | CX (Sales/Service/CPQ) | CX Sales: Leads, Opportunities, Forecasting | CX Sales: Products & Catalog, CX Sales: Territories | Not Started | BLOCKED
cx_svc | 4 | CX (Sales/Service/CPQ) | Fusion Service (Service Requests) | Customer master (Accounts & Sites), CX Sales: Products & Catalog | Not Started | BLOCKED
mnt_maint | 5 | Maintenance & Quality | Maintenance | Inventory orgs & Item Master (PIM), Manufacturing | Not Started | BLOCKED
mnt_qual | 5 | Maintenance & Quality | Quality (Inspection) | Inventory orgs & Item Master (PIM) | Not Started | BLOCKED
cx_cpq | 5 | CX (Sales/Service/CPQ) | CPQ (Configure, Price, Quote) | CX Sales: Leads, Opportunities, Forecasting, Pricing | Not Started | BLOCKED
sub_sub | 5 | CX Subscriptions | Subscription Management | Customer master (Accounts & Sites), Pricing, Receivables (AR) | Not Started | BLOCKED
mktg_elo | 5 | CX Marketing & Eloqua | Marketing & Eloqua | Customer Data Cleansing & TCA load, CX Sales: Leads, Opportunities, Forecasting | Not Started | BLOCKED
prm_prm | 5 | PRM (Partners) | Partner Relationship Management | CX Sales: Leads, Opportunities, Forecasting, Customer master (Accounts & Sites) | Not Started | BLOCKED
icm_part | 5 | ICM (Incentive Comp) | ICM: Participants & roles | CX Sales: Resources & Sales hierarchy, Workforce structures (Legal Employer, Depts, Jobs, Grades) | Not Started | BLOCKED
icm_plan | 6 | ICM (Incentive Comp) | ICM: Plans, Quota & Crediting | ICM: Participants & roles, CX Sales: Territories | Not Started | BLOCKED
icm_txn | 6 | ICM (Incentive Comp) | ICM: Transactions, Calculation & Payment | ICM: Plans, Quota & Crediting, Order Management + Global Order Promising, Receivables (AR) | Not Started | BLOCKED

## 4. Dependencies
Dependency Edges (Task ← requires ← Prerequisite)
Task ID | Task | Phase | Requires (ID) | Requires (Task)
geo | Geographies (TCA) | 1 | — | (foundational — no prerequisites)
ent | Enterprise definition | 1 | geo | Geographies (TCA)
cur | Currencies & conversion rates | 1 | ent | Enterprise definition
coa | Chart of Accounts (segments & value sets) | 1 | cur | Currencies & conversion rates
cal | Accounting calendar | 1 | cur | Currencies & conversion rates
led | Primary Ledger (+ SLA method) | 1 | coa | Chart of Accounts (segments & value sets)
led | Primary Ledger (+ SLA method) | 1 | cal | Accounting calendar
le | Legal Entities & jurisdictions | 1 | led | Primary Ledger (+ SLA method)
bu | Business Units & functions | 1 | le | Legal Entities & jurisdictions
setid | Reference Data Sets (SetID) | 1 | bu | Business Units & functions
loc | Locations | 1 | ent | Enterprise definition
loc | Locations | 1 | geo | Geographies (TCA)
sec | Security: roles, data roles, users | 1 | ent | Enterprise definition
data_clean | Customer Data Cleansing & TCA load | 2 | geo | Geographies (TCA)
cust | Customer master (Accounts & Sites) | 2 | data_clean | Customer Data Cleansing & TCA load
cust | Customer master (Accounts & Sites) | 2 | bu | Business Units & functions
fin_gl | General Ledger | 2 | led | Primary Ledger (+ SLA method)
fin_gl | General Ledger | 2 | sec | Security: roles, data roles, users
fin_tax | Tax | 2 | le | Legal Entities & jurisdictions
fin_tax | Tax | 2 | geo | Geographies (TCA)
scm_sup | Supplier model | 2 | bu | Business Units & functions
scm_sup | Supplier model | 2 | sec | Security: roles, data roles, users
scm_inv | Inventory orgs & Item Master (PIM) | 2 | bu | Business Units & functions
scm_inv | Inventory orgs & Item Master (PIM) | 2 | le | Legal Entities & jurisdictions
hcm_ws | Workforce structures (Legal Employer, Depts, Jobs, Grades) | 2 | bu | Business Units & functions
hcm_ws | Workforce structures (Legal Employer, Depts, Jobs, Grades) | 2 | loc | Locations
fin_cm | Cash Management & Banks | 3 | fin_gl | General Ledger
fin_ap | Payables (AP) | 3 | fin_gl | General Ledger
fin_ap | Payables (AP) | 3 | fin_tax | Tax
fin_ap | Payables (AP) | 3 | scm_sup | Supplier model
fin_ap | Payables (AP) | 3 | fin_cm | Cash Management & Banks
fin_ar | Receivables (AR) | 3 | fin_gl | General Ledger
fin_ar | Receivables (AR) | 3 | fin_tax | Tax
fin_ar | Receivables (AR) | 3 | cust | Customer master (Accounts & Sites)
fin_fa | Fixed Assets (FA) | 3 | fin_gl | General Ledger
scm_price | Pricing | 3 | scm_inv | Inventory orgs & Item Master (PIM)
scm_proc | Purchasing & Self-Service Procurement | 3 | scm_sup | Supplier model
scm_proc | Purchasing & Self-Service Procurement | 3 | scm_inv | Inventory orgs & Item Master (PIM)
hcm_core | Core HR (workers & assignments) | 3 | hcm_ws | Workforce structures (Legal Employer, Depts, Jobs, Grades)
hcm_core | Core HR (workers & assignments) | 3 | sec | Security: roles, data roles, users
cx_res | CX Sales: Resources & Sales hierarchy | 3 | sec | Security: roles, data roles, users
cx_res | CX Sales: Resources & Sales hierarchy | 3 | cust | Customer master (Accounts & Sites)
cx_prod | CX Sales: Products & Catalog | 3 | scm_inv | Inventory orgs & Item Master (PIM)
fin_exp | Expenses | 4 | fin_ap | Payables (AP)
fin_exp | Expenses | 4 | hcm_core | Core HR (workers & assignments)
scm_om | Order Management + Global Order Promising | 4 | scm_inv | Inventory orgs & Item Master (PIM)
scm_om | Order Management + Global Order Promising | 4 | scm_price | Pricing
scm_om | Order Management + Global Order Promising | 4 | cust | Customer master (Accounts & Sites)
scm_om | Order Management + Global Order Promising | 4 | fin_ar | Receivables (AR)
scm_cost | Cost Management | 4 | scm_inv | Inventory orgs & Item Master (PIM)
scm_cost | Cost Management | 4 | fin_gl | General Ledger
scm_mfg | Manufacturing | 4 | scm_inv | Inventory orgs & Item Master (PIM)
hcm_abs | Absence Management | 4 | hcm_core | Core HR (workers & assignments)
hcm_pay | Payroll | 4 | hcm_core | Core HR (workers & assignments)
hcm_cmp | Compensation & Benefits | 4 | hcm_core | Core HR (workers & assignments)
cx_terr | CX Sales: Territories | 4 | cx_res | CX Sales: Resources & Sales hierarchy
cx_terr | CX Sales: Territories | 4 | cust | Customer master (Accounts & Sites)
cx_sales | CX Sales: Leads, Opportunities, Forecasting | 4 | cx_prod | CX Sales: Products & Catalog
cx_sales | CX Sales: Leads, Opportunities, Forecasting | 4 | cx_terr | CX Sales: Territories
cx_svc | Fusion Service (Service Requests) | 4 | cust | Customer master (Accounts & Sites)
cx_svc | Fusion Service (Service Requests) | 4 | cx_prod | CX Sales: Products & Catalog
mnt_maint | Maintenance | 5 | scm_inv | Inventory orgs & Item Master (PIM)
mnt_maint | Maintenance | 5 | scm_mfg | Manufacturing
mnt_qual | Quality (Inspection) | 5 | scm_inv | Inventory orgs & Item Master (PIM)
cx_cpq | CPQ (Configure, Price, Quote) | 5 | cx_sales | CX Sales: Leads, Opportunities, Forecasting
cx_cpq | CPQ (Configure, Price, Quote) | 5 | scm_price | Pricing
sub_sub | Subscription Management | 5 | cust | Customer master (Accounts & Sites)
sub_sub | Subscription Management | 5 | scm_price | Pricing
sub_sub | Subscription Management | 5 | fin_ar | Receivables (AR)
mktg_elo | Marketing & Eloqua | 5 | data_clean | Customer Data Cleansing & TCA load
mktg_elo | Marketing & Eloqua | 5 | cx_sales | CX Sales: Leads, Opportunities, Forecasting
prm_prm | Partner Relationship Management | 5 | cx_sales | CX Sales: Leads, Opportunities, Forecasting
prm_prm | Partner Relationship Management | 5 | cust | Customer master (Accounts & Sites)
icm_part | ICM: Participants & roles | 5 | cx_res | CX Sales: Resources & Sales hierarchy
icm_part | ICM: Participants & roles | 5 | hcm_ws | Workforce structures (Legal Employer, Depts, Jobs, Grades)
icm_plan | ICM: Plans, Quota & Crediting | 6 | icm_part | ICM: Participants & roles
icm_plan | ICM: Plans, Quota & Crediting | 6 | cx_terr | CX Sales: Territories
icm_txn | ICM: Transactions, Calculation & Payment | 6 | icm_plan | ICM: Plans, Quota & Crediting
icm_txn | ICM: Transactions, Calculation & Payment | 6 | scm_om | Order Management + Global Order Promising
icm_txn | ICM: Transactions, Calculation & Payment | 6 | fin_ar | Receivables (AR)

## 5. SQL Validation
SQL — Detect (does it exist?) & Validate (readiness). Run as BI Publisher data-model SQL.
Phase | Pillar | Object | Detect SQL (BIP) | Validate / Readiness Rule
1 | Foundation (Common) | Geographies (TCA) | SELECT 'Geographies' obj, COUNT(*) cnt FROM hz_geographies | Geographies exist for every country used by LE/BU/customers
1 | Foundation (Common) | Enterprise definition | SELECT 'Enterprise' obj, COUNT(*) cnt FROM hr_organization_units hou WHERE hou.organization_type='ENTERPRISE' | Exactly one enterprise defined
1 | Foundation (Common) | Currencies & conversion rates | SELECT 'Enabled Currencies' obj, COUNT(*) cnt FROM fnd_currencies WHERE enabled_flag='Y' | Ledger currency + all transaction currencies enabled; rate types defined
1 | Foundation (Common) | Chart of Accounts (segments & value sets) | SELECT 'COA Structures' obj, COUNT(*) cnt FROM gl_code_combinations WHERE rownum<2 UNION ALL SELECT 'Value Sets', COUNT(*) FROM fnd_vs_value_sets | COA structure + instance defined, all segments mapped to value sets, qualifiers set
1 | Foundation (Common) | Accounting calendar | SELECT 'Calendars' obj, COUNT(DISTINCT period_set_name) cnt FROM gl_periods | Calendar covers conversion history + current + future periods
1 | Foundation (Common) | Primary Ledger (+ SLA method) | SELECT 'Ledgers' obj, COUNT(*) cnt FROM gl_ledgers WHERE ledger_category_code='PRIMARY' | Primary ledger complete and assigned; periods opened
1 | Foundation (Common) | Legal Entities & jurisdictions | SELECT 'Legal Entities' obj, COUNT(*) cnt FROM xle_entity_profiles | Every LE has a registration and is assigned to a ledger
1 | Foundation (Common) | Business Units & functions | SELECT 'Business Units' obj, COUNT(*) cnt FROM fun_all_business_units_v | Each BU has ledger + default LE + required business functions assigned
1 | Foundation (Common) | Reference Data Sets (SetID) | SELECT 'Reference Sets' obj, COUNT(*) cnt FROM fnd_setid_sets | Set determinants assigned for each BU and set-enabled object
1 | Foundation (Common) | Locations | SELECT 'Locations' obj, COUNT(*) cnt FROM per_locations_legislative_g | All operating sites defined with valid geography
1 | Foundation (Common) | Security: roles, data roles, users | SELECT 'Active Users' obj, COUNT(*) cnt FROM per_users WHERE active_flag='Y' | Admin + functional impl users provisioned with correct roles and data scope
2 | Customer Data Cleansing | Customer Data Cleansing & TCA load | SELECT 'Parties' o,COUNT(*) c FROM hz_parties UNION ALL SELECT 'Cust Accounts',COUNT(*) FROM hz_cust_accounts | Golden party set deduped, standardized, hierarchy built, ready to load
2 | Customer Data Cleansing | Customer master (Accounts & Sites) | SELECT 'Customer Sites' obj, COUNT(*) cnt FROM hz_cust_acct_sites_all | Accounts + sites + uses loaded; reconciled to golden set; no dupes
2 | ERP / Financials | General Ledger | SELECT 'GL Journals' obj, COUNT(*) cnt FROM gl_je_headers WHERE rownum<2 | Period open, journal import working, opening balances loaded & reconciled
2 | ERP / Financials | Tax | SELECT 'Tax Regimes' obj, COUNT(*) cnt FROM zx_regimes_b | Regimes/rates/rules tested on sample AP & AR transactions
2 | SCM / Procurement / Mfg | Supplier model | SELECT 'Suppliers' obj, COUNT(*) cnt FROM poz_suppliers | Suppliers + sites + bank accounts loaded & deduped
2 | SCM / Procurement / Mfg | Inventory orgs & Item Master (PIM) | SELECT 'Inv Orgs' o,COUNT(*) c FROM inv_org_parameters UNION ALL SELECT 'Items',COUNT(*) FROM egp_system_items_b | Inventory orgs created; item master loaded with required attributes
2 | HCM | Workforce structures (Legal Employer, Depts, Jobs, Grades) | SELECT 'Departments' o,COUNT(*) c FROM per_departments UNION ALL SELECT 'Jobs',COUNT(*) FROM per_jobs_f UNION ALL SELECT 'Grades',COUNT(*) FROM per_grades_f | Legal employer(s), department tree, jobs/positions, grades all defined
3 | ERP / Financials | Cash Management & Banks | SELECT 'Bank Accounts' obj, COUNT(*) cnt FROM ce_bank_accounts | Bank accounts set up, statement import & reconciliation tested
3 | ERP / Financials | Payables (AP) | SELECT 'AP Invoices' obj, COUNT(*) cnt FROM ap_invoices_all WHERE rownum<2 | Payment process tested; open invoices loaded & reconciled
3 | ERP / Financials | Receivables (AR) | SELECT 'AR Transactions' obj, COUNT(*) cnt FROM ra_customer_trx_all WHERE rownum<2 | AutoInvoice + receipts tested; open AR loaded & reconciled
3 | ERP / Financials | Fixed Assets (FA) | SELECT 'FA Books' obj, COUNT(*) cnt FROM fa_book_controls | Books & categories defined; asset conversion loaded; depreciation tested
3 | SCM / Procurement / Mfg | Pricing | SELECT 'Price Lists' obj, COUNT(*) cnt FROM qp_pricing_pte_v WHERE rownum<2 | Price lists loaded; pricing returns correct results on test orders
3 | SCM / Procurement / Mfg | Purchasing & Self-Service Procurement | SELECT 'Purchase Orders' obj, COUNT(*) cnt FROM po_headers_all WHERE rownum<2 | Req-to-PO-to-receipt tested; agreements loaded
3 | HCM | Core HR (workers & assignments) | SELECT 'Workers' obj, COUNT(*) cnt FROM per_all_people_f | Active worker assignments loaded and reconciled to source
3 | CX (Sales/Service/CPQ) | CX Sales: Resources & Sales hierarchy | SELECT 'Sales Resources' obj, COUNT(*) cnt FROM zmm_resources_v WHERE rownum<2 | Resource org + hierarchy built; resources active
3 | CX (Sales/Service/CPQ) | CX Sales: Products & Catalog | SELECT 'Sales Products' obj, COUNT(*) cnt FROM qsc_products_v WHERE rownum<2 | Sales catalog published and usable on opportunities
4 | ERP / Financials | Expenses | SELECT 'Expense Reports' obj, COUNT(*) cnt FROM exm_expense_reports WHERE rownum<2 | Expense submission → AP invoice tested end to end
4 | SCM / Procurement / Mfg | Order Management + Global Order Promising | SELECT 'Sales Orders' obj, COUNT(*) cnt FROM doo_headers_all WHERE rownum<2 | Order-to-cash flow tested across OM → fulfillment → AR
4 | SCM / Procurement / Mfg | Cost Management | SELECT 'Cost Orgs' obj, COUNT(*) cnt FROM cst_cost_org_books WHERE rownum<2 | Cost accounting runs clean; distributions post to GL
4 | SCM / Procurement / Mfg | Manufacturing | SELECT 'Work Orders' obj, COUNT(*) cnt FROM wie_work_orders_b WHERE rownum<2 | Work order execution tested
4 | HCM | Absence Management | SELECT 'Absence Plans' obj, COUNT(*) cnt FROM anc_absence_plans_f | Plans configured and enrolled
4 | HCM | Payroll | SELECT 'Payroll Defns' obj, COUNT(*) cnt FROM pay_all_payrolls_f | Payroll definitions, elements, costing, and a clean test run complete
4 | HCM | Compensation & Benefits | SELECT 'Comp Plans' obj, COUNT(*) cnt FROM cmp_salary_bases | Plans and eligibility configured; test enrollments pass
4 | CX (Sales/Service/CPQ) | CX Sales: Territories | SELECT 'Territories' obj, COUNT(*) cnt FROM moo_terr_all_v WHERE rownum<2 | Territories proposed/activated; assignment runs correctly
4 | CX (Sales/Service/CPQ) | CX Sales: Leads, Opportunities, Forecasting | SELECT 'Opportunities' obj, COUNT(*) cnt FROM moo_opty_all_b WHERE rownum<2 | Lead→Opty→Forecast flow tested with real users
4 | CX (Sales/Service/CPQ) | Fusion Service (Service Requests) | SELECT 'Service Requests' obj, COUNT(*) cnt FROM svc_service_requests WHERE rownum<2 | SR intake → routing → SLA → resolution tested
5 | Maintenance & Quality | Maintenance | SELECT 'Maint Work Orders' obj, COUNT(*) cnt FROM mnt_work_orders_b WHERE rownum<2 | Asset + PM program + work order execution tested
5 | Maintenance & Quality | Quality (Inspection) | SELECT 'Inspection Plans' obj, COUNT(*) cnt FROM qa_plans WHERE rownum<2 | Inspection plans execute and capture results at chosen points
5 | CX (Sales/Service/CPQ) | CPQ (Configure, Price, Quote) | SELECT 'CPQ Quotes' obj, COUNT(*) cnt FROM /* CPQ is separate stack */ dual | Quote → approval → order integration tested
5 | CX Subscriptions | Subscription Management | SELECT 'Subscriptions' obj, COUNT(*) cnt FROM oss_subscriptions WHERE rownum<2 | Subscription → bill → AR invoice → revenue tested end to end
5 | CX Marketing & Eloqua | Marketing & Eloqua | SELECT 'Marketing Leads' obj, COUNT(*) cnt FROM mkt_leads WHERE rownum<2 | Contact sync + scoring + lead handoff to Sales tested
5 | PRM (Partners) | Partner Relationship Management | SELECT 'Partner Accounts' obj, COUNT(*) cnt FROM zpm_partners_v WHERE rownum<2 | Partner onboarding + deal reg + portal tested
5 | ICM (Incentive Comp) | ICM: Participants & roles | SELECT 'ICM Participants' obj, COUNT(*) cnt FROM cn_srp_periods_all WHERE rownum<2 | Participants loaded with roles, pay groups, and hierarchy
6 | ICM (Incentive Comp) | ICM: Plans, Quota & Crediting | SELECT 'Comp Plans' obj, COUNT(*) cnt FROM cn_comp_plans_all_b WHERE rownum<2 | Plans assigned, quotas loaded, crediting validated on sample
6 | ICM (Incentive Comp) | ICM: Transactions, Calculation & Payment | SELECT 'Comp Transactions' obj, COUNT(*) cnt FROM cn_tp_transactions_all WHERE rownum<2 | Import → calculate → approve → pay tested with reconciled amounts

## 6. Dashboard
Implementation Dashboard
Overall
Total tasks | 46
Done | 0
In Progress | 0
Not Started | 46
Blocked (flagged) | 45
% Complete | 0%
By Pillar |  |  |  | By Phase
Pillar | Total | Done | % Done | Phase | Total | Done | % Done
Foundation (Common) | 11 | 0 | 0% | 1 | 11 | 0 | 0%
Customer Data Cleansing | 2 | 0 | 0% | 2 | 7 | 0 | 0%
ERP / Financials | 7 | 0 | 0% | 3 | 9 | 0 | 0%
SCM / Procurement / Mfg | 7 | 0 | 0% | 4 | 10 | 0 | 0%
Maintenance & Quality | 2 | 0 | 0% | 5 | 7 | 0 | 0%
HCM | 5 | 0 | 0% | 6 | 2 | 0 | 0%
CX (Sales/Service/CPQ) | 6 | 0 | 0%
CX Subscriptions | 1 | 0 | 0%
CX Marketing & Eloqua | 1 | 0 | 0%
PRM (Partners) | 1 | 0 | 0%
ICM (Incentive Comp) | 3 | 0 | 0%