Oracle Fusion Pod

SI Implementation Playbook

From a freshly provisioned pod to a sequenced, dependency-driven, multi-pillar implementation. A guide for the SI Business Architect to drive — and the client to follow.

Scope: HCM · ERP/Financials · SCM/Procurement · Maintenance & Quality · CX (Sales/Service/CPQ) · Subscriptions · Marketing/Eloqua · PRM · ICM · Customer Data Cleansing

Prepared for: Chandra Kasarabada — Argano

# Contents

# 1. How to run this as the SI Business Architect

This playbook sequences a Fusion program the way it must actually be built: foundation before modules, master data before transactions, and every module gated by its dependencies. The companion interactive guide and the Excel tracker share the exact same 46-task model — use this document for the narrative and rationale, the tracker for status and RACI, and the interactive guide to run discovery and detect pod state live.

## The five operating principles

- Discovery first. Do not open Functional Setup Manager until the chart of accounts, ledger, legal-entity/business-unit, and calendar decisions are made. Re-keying these later is a re-implementation, not a change.

- Lock the Foundation. Enterprise structures, security, and geographies must be complete and validated (all readiness rules PASS) before any business-process module begins. This is the single biggest cause of failed Fusion programs.

- Sequence by dependency, not by enthusiasm. The client will want to start with the most visible module. The roadmap enforces what genuinely has to come first.

- Convert data in waves. Foundation reference data, then master data (customers, suppliers, items, workers), then open transactions and balances. Reconcile each wave against the pod with the detect queries.

- The test pod is sacred. Every load and every configuration proves out in test, then moves to production through configuration packages aligned to your P2T strategy.

# 2. Phase 0 — Post-Provisioning Install & Access

Done once, before any functional setup. The goal is a usable, secured pod with the right offerings switched on and a clear path from test to production.

| # | Step | What it covers |
| --- | --- | --- |
| 1 | Receive pod details & service admin access | Capture test & prod pod URLs, identity domain, and the initial service administrator credentials from the activation email. |
| 2 | Configure identity (IAM/IDCS) & SSO | Set up the identity domain, federation/SSO with the client IdP, password policy, and MFA. Provision the first implementation users. |
| 3 | Security Console baseline | Copy seeded roles to custom roles, set role hierarchy strategy, and define the data-security approach before provisioning functional users. |
| 4 | Outbound email & notifications | Configure email server / from-address, BI delivery, and approval notifications so workflows and reports can send. |
| 5 | Environment strategy (Test ↔ Prod, P2T) | Confirm number of environments, refresh (P2T) cadence, and how config moves (configuration packages / migration sets) test→prod. |
| 6 | Enable offerings in Functional Setup Manager | Turn on the offerings for in-scope pillars (Financials, Procurement, SCM, HCM, CX, etc.). This is the master switch that reveals setup tasks. |
| 7 | Create implementation project & setup strategy | Decide UI task-list vs export/import setup, define the implementation project, and assign setup task owners. |
| 8 | Sandbox & extensibility strategy | Establish sandbox naming/governance for page/object extensions and the publish workflow. |
| 9 | Release readiness process | Set the process for quarterly Fusion updates: read what's new, regression test in test pod, then apply to prod. |

# 3. Discovery — the decisions that anchor everything

Run these with the client before configuration. You are capturing decisions, not just collecting data. The items below are the design-critical questions; the interactive guide and tracker carry the full per-module question banks.

### Foundation (Common) — Chart of Accounts (segments & value sets)

The single most consequential design decision in Fusion ERP. Segments, value sets, hierarchies. Changing it post-go-live is a re-implementation.

- How many segments and what (Company, Cost Center, Account, Product, Intercompany, Future)?

- Segment lengths & value set sizes?

- Hierarchies/trees needed for reporting?

- Natural account = account segment qualifier?

### Foundation (Common) — Primary Ledger (+ SLA method)

Binds COA + Calendar + Currency + Subledger Accounting Method. The accounting backbone every financial transaction posts to.

- One ledger or many (multi-country)?

- Accounting method (Standard Accrual)?

- Secondary ledger / reporting currency needed?

- Ledger set / balancing rules?

### Foundation (Common) — Legal Entities & jurisdictions

Legal owners of transactions; drive tax registration and statutory reporting. Assigned to the ledger.

- How many legal entities / countries?

- Registration numbers & jurisdictions?

- Which LE is the ledger's default?

### Foundation (Common) — Business Units & functions

Operational partitions for AP/AR/Procurement/OM. Each BU gets a default LE, ledger, and enabled business functions.

- How many BUs and on what basis (geo, line of business, shared services)?

- Which functions per BU (Payables, Receivables, Procurement, OM, Billing)?

- Shared service center model?

### Foundation (Common) — Reference Data Sets (SetID)

Controls how reference data (payment terms, receipt methods, etc.) is shared vs partitioned across BUs.

- Common set for all, or partitioned reference data?

- Which set-enabled objects need partitioning?

### Foundation (Common) — Security: roles, data roles, users

Role-based access control. Provision implementation users, define data security (BU/LE scoping), abstract/job/duty roles, SoD.

- SSO/IDCS federation or local accounts?

- Role mapping per persona?

- Data scoping by BU/LE/business unit security?

- SoD policy / audit requirements?

### Customer Data Cleansing — Customer Data Cleansing & TCA load

Standardize, dedupe, and enrich party data BEFORE loading customers. Everything customer-facing (AR, OM, CX, Subscriptions, PRM) inherits this quality. Get TCA right once.

- Source systems & record counts?

- Dedup/match rules & survivorship?

- Account vs party hierarchy needed?

- Address validation source?

- Sales account vs customer (AR) account split understood?

### Customer Data Cleansing — Customer master (Accounts & Sites)

Loaded TCA customer accounts, sites, bill-to/ship-to. Prereq for AR, OM, CX Sales, Subscriptions, PRM.

- Bill-to/ship-to site model?

- Account hierarchy/parenting?

- Payment terms per account/site?

- Sales account assignment for CX?

### SCM / Procurement / Mfg — Inventory orgs & Item Master (PIM)

Inventory organizations, item master/PIM. Core master data for OM, Cost, Mfg, Maintenance, Subscriptions, CPQ.

- Inventory org structure (master + child)?

- Item classes & attributes?

- Catalogs & categories?

- Conversion source for items?

### HCM — Workforce structures (Legal Employer, Depts, Jobs, Grades)

Legal employer, departments, jobs, positions, grades — the skeleton every worker assignment hangs on. Also feeds Sales resources and ICM participants.

- Job vs position management?

- Department tree?

- Grades & grade ladders?

- Legal employers per country?

# 4. The Foundation (Phase 1) — enterprise structures & security

Build in this order. Each item depends on the one(s) before it; skipping ahead creates rework that cascades through every pillar.

| Step | Foundation object | Depends on | Why it matters |
| --- | --- | --- | --- |
| 1 | Geographies (TCA) | — | Master geography tree underpins address validation, tax jurisdictions, sales territories and customer/supplier addresses. Load before any party data. |
| 2 | Enterprise definition | Geographies (TCA) | Top of the organization model. One enterprise per pod. Sets name, location, and HCM enterprise information. |
| 3 | Currencies & conversion rates | Enterprise definition | Enable transacting currencies and rate types before defining ledgers and pricing. |
| 4 | Chart of Accounts (segments & value sets) | Currencies & conversion rates | The single most consequential design decision in Fusion ERP. Segments, value sets, hierarchies. Changing it post-go-live is a re-implementation. |
| 5 | Accounting calendar | Currencies & conversion rates | Defines accounting periods. Must align with fiscal year before the ledger is created. |
| 6 | Primary Ledger (+ SLA method) | Chart of Accounts (segments & value sets), Accounting calendar | Binds COA + Calendar + Currency + Subledger Accounting Method. The accounting backbone every financial transaction posts to. |
| 7 | Legal Entities & jurisdictions | Primary Ledger (+ SLA method) | Legal owners of transactions; drive tax registration and statutory reporting. Assigned to the ledger. |
| 8 | Business Units & functions | Legal Entities & jurisdictions | Operational partitions for AP/AR/Procurement/OM. Each BU gets a default LE, ledger, and enabled business functions. |
| 9 | Reference Data Sets (SetID) | Business Units & functions | Controls how reference data (payment terms, receipt methods, etc.) is shared vs partitioned across BUs. |
| 10 | Locations | Enterprise definition, Geographies (TCA) | Physical/work locations referenced by HCM departments, inventory orgs, and LEs. |
| 11 | Security: roles, data roles, users | Enterprise definition | Role-based access control. Provision implementation users, define data security (BU/LE scoping), abstract/job/duty roles, SoD. |

Gate: Do not start Phase 2 until every Foundation readiness rule returns PASS (see Appendix B).

# 5. Module roadmap by phase

After the Foundation, modules unlock by dependency across the phases below. A module is 'ready' only when all its prerequisites are Done.

## Phase 1 — Foundation — Enterprise Structures & Security

| Pillar | Module | Prerequisites |
| --- | --- | --- |
| Foundation (Common) | Geographies (TCA) | — |
| Foundation (Common) | Enterprise definition | Geographies (TCA) |
| Foundation (Common) | Currencies & conversion rates | Enterprise definition |
| Foundation (Common) | Chart of Accounts (segments & value sets) | Currencies & conversion rates |
| Foundation (Common) | Accounting calendar | Currencies & conversion rates |
| Foundation (Common) | Primary Ledger (+ SLA method) | Chart of Accounts (segments & value sets), Accounting calendar |
| Foundation (Common) | Legal Entities & jurisdictions | Primary Ledger (+ SLA method) |
| Foundation (Common) | Business Units & functions | Legal Entities & jurisdictions |
| Foundation (Common) | Reference Data Sets (SetID) | Business Units & functions |
| Foundation (Common) | Locations | Enterprise definition, Geographies (TCA) |
| Foundation (Common) | Security: roles, data roles, users | Enterprise definition |

## Phase 2 — Pillar foundations & master data

| Pillar | Module | Prerequisites |
| --- | --- | --- |
| HCM | Workforce structures (Legal Employer, Depts, Jobs, Grades) | Business Units & functions, Locations |
| ERP / Financials | General Ledger | Primary Ledger (+ SLA method), Security: roles, data roles, users |
| ERP / Financials | Tax | Legal Entities & jurisdictions, Geographies (TCA) |
| SCM / Procurement / Mfg | Supplier model | Business Units & functions, Security: roles, data roles, users |
| SCM / Procurement / Mfg | Inventory orgs & Item Master (PIM) | Business Units & functions, Legal Entities & jurisdictions |
| Customer Data Cleansing | Customer Data Cleansing & TCA load | Geographies (TCA) |
| Customer Data Cleansing | Customer master (Accounts & Sites) | Customer Data Cleansing & TCA load, Business Units & functions |

## Phase 3 — Core transactional modules

| Pillar | Module | Prerequisites |
| --- | --- | --- |
| HCM | Core HR (workers & assignments) | Workforce structures (Legal Employer, Depts, Jobs, Grades), Security: roles, data roles, users |
| ERP / Financials | Cash Management & Banks | General Ledger |
| ERP / Financials | Payables (AP) | General Ledger, Tax, Supplier model, Cash Management & Banks |
| ERP / Financials | Receivables (AR) | General Ledger, Tax, Customer master (Accounts & Sites) |
| ERP / Financials | Fixed Assets (FA) | General Ledger |
| SCM / Procurement / Mfg | Pricing | Inventory orgs & Item Master (PIM) |
| SCM / Procurement / Mfg | Purchasing & Self-Service Procurement | Supplier model, Inventory orgs & Item Master (PIM) |
| CX (Sales/Service/CPQ) | CX Sales: Resources & Sales hierarchy | Security: roles, data roles, users, Customer master (Accounts & Sites) |
| CX (Sales/Service/CPQ) | CX Sales: Products & Catalog | Inventory orgs & Item Master (PIM) |

## Phase 4 — Operational modules

| Pillar | Module | Prerequisites |
| --- | --- | --- |
| HCM | Absence Management | Core HR (workers & assignments) |
| HCM | Payroll | Core HR (workers & assignments) |
| HCM | Compensation & Benefits | Core HR (workers & assignments) |
| ERP / Financials | Expenses | Payables (AP), Core HR (workers & assignments) |
| SCM / Procurement / Mfg | Order Management + Global Order Promising | Inventory orgs & Item Master (PIM), Pricing, Customer master (Accounts & Sites), Receivables (AR) |
| SCM / Procurement / Mfg | Cost Management | Inventory orgs & Item Master (PIM), General Ledger |
| SCM / Procurement / Mfg | Manufacturing | Inventory orgs & Item Master (PIM) |
| CX (Sales/Service/CPQ) | CX Sales: Territories | CX Sales: Resources & Sales hierarchy, Customer master (Accounts & Sites) |
| CX (Sales/Service/CPQ) | CX Sales: Leads, Opportunities, Forecasting | CX Sales: Products & Catalog, CX Sales: Territories |
| CX (Sales/Service/CPQ) | Fusion Service (Service Requests) | Customer master (Accounts & Sites), CX Sales: Products & Catalog |

## Phase 5 — Advanced / channel modules

| Pillar | Module | Prerequisites |
| --- | --- | --- |
| Maintenance & Quality | Maintenance | Inventory orgs & Item Master (PIM), Manufacturing |
| Maintenance & Quality | Quality (Inspection) | Inventory orgs & Item Master (PIM) |
| CX (Sales/Service/CPQ) | CPQ (Configure, Price, Quote) | CX Sales: Leads, Opportunities, Forecasting, Pricing |
| CX Subscriptions | Subscription Management | Customer master (Accounts & Sites), Pricing, Receivables (AR) |
| CX Marketing & Eloqua | Marketing & Eloqua | Customer Data Cleansing & TCA load, CX Sales: Leads, Opportunities, Forecasting |
| PRM (Partners) | Partner Relationship Management | CX Sales: Leads, Opportunities, Forecasting, Customer master (Accounts & Sites) |
| ICM (Incentive Comp) | ICM: Participants & roles | CX Sales: Resources & Sales hierarchy, Workforce structures (Legal Employer, Depts, Jobs, Grades) |

## Phase 6 — Compensation calculation

| Pillar | Module | Prerequisites |
| --- | --- | --- |
| ICM (Incentive Comp) | ICM: Plans, Quota & Crediting | ICM: Participants & roles, CX Sales: Territories |
| ICM (Incentive Comp) | ICM: Transactions, Calculation & Payment | ICM: Plans, Quota & Crediting, Order Management + Global Order Promising, Receivables (AR) |

# 6. Cross-pillar dependency cheatsheet

These are the dependencies that cross pillar boundaries — the ones most often missed in planning because each pillar team only sees its own backlog.

| Module | Needs first (cross-pillar) |
| --- | --- |
| ICM (Incentive Comp) | HCM/Sales resources (participants) · OM/AR transactions to credit · Territories · Plans & Quota |
| Expenses | HCM workers · AP · payment terms |
| Order Management | Inventory orgs · Items/Pricing · Customers (TCA) · AR for billing · Global Order Promising |
| Subscriptions | Products/Items · Pricing · Customers · AR/Invoicing · Revenue Management |
| CPQ | Products · Pricing · CX Sales accounts & opportunities |
| PRM | CX Sales · Partner accounts (TCA) · Programs / Deal Registration |
| Maintenance / Quality | Inventory · Assets/Items · Work orders (Manufacturing) |
| Marketing / Eloqua | Clean contact & lead data · CX Sales integration · Customer master |

# 7. Data conversion & the SQL toolkit

Fusion blocks direct database SQL on shipped pods. Run the queries in this playbook as BI Publisher data-model SQL, or rebuild them as OTBI analyses. They serve four jobs:

- Detect current pod state — find out what is already configured so you skip done steps.

- Validate completeness — confirm the Foundation is correctly set before unlocking modules.

- FBDI bulk-load templates — load setup and master data in volume (customers, suppliers, items, workers, balances).

- Excel → SQL / REST — convert the client's spreadsheets into staging inserts and REST payloads, mapped to Fusion attributes.

## Conversion waves

- Foundation reference data (geographies, COA values, calendars).

- Master data — customers (after cleansing), suppliers, items, workers.

- Open transactions and opening balances (GL, AP, AR, inventory, assets).

Reconcile each wave with the detect queries before moving to the next. Load into the test pod first; never convert straight to production.

## Common FBDI templates

| Object | FBDI template | Import process |
| --- | --- | --- |
| Chart of Accounts values | ChartOfAccountsValuesImportTemplate.xlsm | Import CoA Segment Values & Hierarchies |
| GL journals / balances | JournalImportTemplate.xlsm | Import Journals |
| Suppliers | SupplierImportTemplate.xlsm | Import Suppliers (+ Sites, Contacts, Bank Accts) |
| Customers / TCA parties | Trading Community import templates | Import Person/Org / Customer Account |
| Items (PIM) | ScmItemImportTemplate.xlsm | Item Import |
| Workers (HCM) | HCM Data Loader (.dat) / HSDL | Load Worker / Initiate HDL |

# Appendix A — Module reference (all pillars)

Every task in the model, with its prerequisites, discovery questions, and load approach.

### Geographies (TCA)  ·  Foundation (Common) · Phase 1

Master geography tree underpins address validation, tax jurisdictions, sales territories and customer/supplier addresses. Load before any party data.

Prerequisites: None (foundational)

Discovery: Which countries are in scope?  ·  Do you need address validation / cleansing?  ·  Licensed geography reference data (Loqate/Nokia) or manual?

Validate: Geographies exist for every country used by LE/BU/customers

Load: Manage Geographies UI + Loqate/Nokia reference, or HZ geography import.

### Enterprise definition  ·  Foundation (Common) · Phase 1

Top of the organization model. One enterprise per pod. Sets name, location, and HCM enterprise information.

Prerequisites: Geographies (TCA)

Discovery: Legal/registered enterprise name?  ·  Primary enterprise location?  ·  Single enterprise across all LEs? (almost always yes)

Validate: Exactly one enterprise defined

Load: Manage Enterprise HCM Information (UI).

### Currencies & conversion rates  ·  Foundation (Common) · Phase 1

Enable transacting currencies and rate types before defining ledgers and pricing.

Prerequisites: Enterprise definition

Discovery: Functional/ledger currency?  ·  Foreign currencies transacted?  ·  Daily/Corporate/Spot rate types and source?

Validate: Ledger currency + all transaction currencies enabled; rate types defined

Load: Manage Currencies / Conversion Rate Types; GL Daily Rates FBDI for rates.

### Chart of Accounts (segments & value sets)  ·  Foundation (Common) · Phase 1

The single most consequential design decision in Fusion ERP. Segments, value sets, hierarchies. Changing it post-go-live is a re-implementation.

Prerequisites: Currencies & conversion rates

Discovery: How many segments and what (Company, Cost Center, Account, Product, Intercompany, Future)?  ·  Segment lengths & value set sizes?  ·  Hierarchies/trees needed for reporting?  ·  Natural account = account segment qualifier?

Validate: COA structure + instance defined, all segments mapped to value sets, qualifiers set

Load: Manage CoA Structure/Instance; ChartOfAccountsValues FBDI for segment values & hierarchies.

### Accounting calendar  ·  Foundation (Common) · Phase 1

Defines accounting periods. Must align with fiscal year before the ledger is created.

Prerequisites: Currencies & conversion rates

Discovery: Fiscal year start month?  ·  Period frequency (monthly/4-4-5)?  ·  How many adjusting periods?  ·  History years to open?

Validate: Calendar covers conversion history + current + future periods

Load: Manage Accounting Calendars (UI).

### Primary Ledger (+ SLA method)  ·  Foundation (Common) · Phase 1

Binds COA + Calendar + Currency + Subledger Accounting Method. The accounting backbone every financial transaction posts to.

Prerequisites: Chart of Accounts (segments & value sets), Accounting calendar

Discovery: One ledger or many (multi-country)?  ·  Accounting method (Standard Accrual)?  ·  Secondary ledger / reporting currency needed?  ·  Ledger set / balancing rules?

Validate: Primary ledger complete and assigned; periods opened

Load: Define Ledger task list; complete configuration; open first period.

### Legal Entities & jurisdictions  ·  Foundation (Common) · Phase 1

Legal owners of transactions; drive tax registration and statutory reporting. Assigned to the ledger.

Prerequisites: Primary Ledger (+ SLA method)

Discovery: How many legal entities / countries?  ·  Registration numbers & jurisdictions?  ·  Which LE is the ledger's default?

Validate: Every LE has a registration and is assigned to a ledger

Load: Manage Legal Entity / Registrations / Legal Reporting Units (UI).

### Business Units & functions  ·  Foundation (Common) · Phase 1

Operational partitions for AP/AR/Procurement/OM. Each BU gets a default LE, ledger, and enabled business functions.

Prerequisites: Legal Entities & jurisdictions

Discovery: How many BUs and on what basis (geo, line of business, shared services)?  ·  Which functions per BU (Payables, Receivables, Procurement, OM, Billing)?  ·  Shared service center model?

Validate: Each BU has ledger + default LE + required business functions assigned

Load: Manage Business Unit + Assign Business Function (UI).

### Reference Data Sets (SetID)  ·  Foundation (Common) · Phase 1

Controls how reference data (payment terms, receipt methods, etc.) is shared vs partitioned across BUs.

Prerequisites: Business Units & functions

Discovery: Common set for all, or partitioned reference data?  ·  Which set-enabled objects need partitioning?

Validate: Set determinants assigned for each BU and set-enabled object

Load: Manage Reference Data Sets + Set Assignments (UI).

### Locations  ·  Foundation (Common) · Phase 1

Physical/work locations referenced by HCM departments, inventory orgs, and LEs.

Prerequisites: Enterprise definition, Geographies (TCA)

Discovery: List of physical sites?  ·  Which are inventory/ship-from locations?

Validate: All operating sites defined with valid geography

Load: Manage Locations (UI) or HCM Data Loader.

### Security: roles, data roles, users  ·  Foundation (Common) · Phase 1

Role-based access control. Provision implementation users, define data security (BU/LE scoping), abstract/job/duty roles, SoD.

Prerequisites: Enterprise definition

Discovery: SSO/IDCS federation or local accounts?  ·  Role mapping per persona?  ·  Data scoping by BU/LE/business unit security?  ·  SoD policy / audit requirements?

Validate: Admin + functional impl users provisioned with correct roles and data scope

Load: Security Console: roles & role copy; user provisioning; HCM/Data security profiles.

### Customer Data Cleansing & TCA load  ·  Customer Data Cleansing · Phase 2

Standardize, dedupe, and enrich party data BEFORE loading customers. Everything customer-facing (AR, OM, CX, Subscriptions, PRM) inherits this quality. Get TCA right once.

Prerequisites: Geographies (TCA)

Discovery: Source systems & record counts?  ·  Dedup/match rules & survivorship?  ·  Account vs party hierarchy needed?  ·  Address validation source?  ·  Sales account vs customer (AR) account split understood?

Validate: Golden party set deduped, standardized, hierarchy built, ready to load

Load: Profiling → match/merge → enrich. Load via HZ Import FBDI / REST.

### Customer master (Accounts & Sites)  ·  Customer Data Cleansing · Phase 2

Loaded TCA customer accounts, sites, bill-to/ship-to. Prereq for AR, OM, CX Sales, Subscriptions, PRM.

Prerequisites: Customer Data Cleansing & TCA load, Business Units & functions

Discovery: Bill-to/ship-to site model?  ·  Account hierarchy/parenting?  ·  Payment terms per account/site?  ·  Sales account assignment for CX?

Validate: Accounts + sites + uses loaded; reconciled to golden set; no dupes

Load: Customer/Account Import FBDI or TCA REST.

### General Ledger  ·  ERP / Financials · Phase 2

First financial module live. Journals, allocations, period close, financial reporting (FRS/SmartView).

Prerequisites: Primary Ledger (+ SLA method), Security: roles, data roles, users

Discovery: Manual vs imported journals?  ·  Allocation rules?  ·  Close calendar & approvals?  ·  Reporting (FRS, Account Inspector)?

Validate: Period open, journal import working, opening balances loaded & reconciled

Load: GL config tasks; Journal Import FBDI; balances via FBDI.

### Tax  ·  ERP / Financials · Phase 2

Tax regimes, statuses, rates, rules — required before AP/AR can compute tax on transactions.

Prerequisites: Legal Entities & jurisdictions, Geographies (TCA)

Discovery: Tax regimes & countries?  ·  Self-assessment / reverse charge?  ·  Tax partner (Vertex/OneSource)?

Validate: Regimes/rates/rules tested on sample AP & AR transactions

Load: Manage Tax tasks; Tax rates FBDI; or tax partner integration.

### Supplier model  ·  SCM / Procurement / Mfg · Phase 2

Supplier master + sites + bank accounts. Needed by Payables and Purchasing.

Prerequisites: Business Units & functions, Security: roles, data roles, users

Discovery: Supplier count & conversion source?  ·  Self-service supplier portal?  ·  Bank/payment detail?  ·  Qualification needed?

Validate: Suppliers + sites + bank accounts loaded & deduped

Load: Supplier Import FBDI (supplier, sites, contacts, bank accts) or Supplier REST.

### Inventory orgs & Item Master (PIM)  ·  SCM / Procurement / Mfg · Phase 2

Inventory organizations, item master/PIM. Core master data for OM, Cost, Mfg, Maintenance, Subscriptions, CPQ.

Prerequisites: Business Units & functions, Legal Entities & jurisdictions

Discovery: Inventory org structure (master + child)?  ·  Item classes & attributes?  ·  Catalogs & categories?  ·  Conversion source for items?

Validate: Inventory orgs created; item master loaded with required attributes

Load: Configure Inventory Orgs; Item Import FBDI / Product Data Hub.

### Workforce structures (Legal Employer, Depts, Jobs, Grades)  ·  HCM · Phase 2

Legal employer, departments, jobs, positions, grades — the skeleton every worker assignment hangs on. Also feeds Sales resources and ICM participants.

Prerequisites: Business Units & functions, Locations

Discovery: Job vs position management?  ·  Department tree?  ·  Grades & grade ladders?  ·  Legal employers per country?

Validate: Legal employer(s), department tree, jobs/positions, grades all defined

Load: Manage tasks in Workforce Structures; HCM Data Loader for bulk.

### Cash Management & Banks  ·  ERP / Financials · Phase 3

Bank accounts, statements, reconciliation. Needed by AP payments and AR receipts.

Prerequisites: General Ledger

Discovery: Banks/branches/accounts?  ·  Statement formats & auto-reconciliation?  ·  Payment file formats?

Validate: Bank accounts set up, statement import & reconciliation tested

Load: Cash Mgmt setup; Banks/Branches/Accounts FBDI.

### Payables (AP)  ·  ERP / Financials · Phase 3

Invoices, payments, expense integration. Depends on suppliers, tax, banks, GL.

Prerequisites: General Ledger, Tax, Supplier model, Cash Management & Banks

Discovery: Invoice approval workflow?  ·  Payment terms & methods?  ·  Withholding tax?  ·  Open invoice conversion?

Validate: Payment process tested; open invoices loaded & reconciled

Load: Payables config; Payables Invoice & Payments FBDI.

### Receivables (AR)  ·  ERP / Financials · Phase 3

Invoices, receipts, revenue. Depends on customers (TCA), tax, GL. Foundation for Subscriptions billing.

Prerequisites: General Ledger, Tax, Customer master (Accounts & Sites)

Discovery: Transaction types & sources?  ·  Receipt methods & lockbox?  ·  AutoInvoice from OM/Subscriptions?  ·  Open AR conversion?

Validate: AutoInvoice + receipts tested; open AR loaded & reconciled

Load: Receivables config; AutoInvoice FBDI; receipts FBDI.

### Fixed Assets (FA)  ·  ERP / Financials · Phase 3

Asset books, categories, depreciation. Depends on GL.

Prerequisites: General Ledger

Discovery: Corporate & tax books?  ·  Asset categories & depreciation methods?  ·  Mass additions from AP?

Validate: Books & categories defined; asset conversion loaded; depreciation tested

Load: Assets config; Mass Additions / FA FBDI.

### Pricing  ·  SCM / Procurement / Mfg · Phase 3

Price lists, discounts, pricing strategies. Shared by OM, CPQ, Subscriptions.

Prerequisites: Inventory orgs & Item Master (PIM)

Discovery: Price list structure & currencies?  ·  Discount/charge rules?  ·  Pricing strategy assignment?

Validate: Price lists loaded; pricing returns correct results on test orders

Load: Pricing Administration; Price List import.

### Purchasing & Self-Service Procurement  ·  SCM / Procurement / Mfg · Phase 3

Requisitions, POs, agreements, approvals. Depends on suppliers & items.

Prerequisites: Supplier model, Inventory orgs & Item Master (PIM)

Discovery: Requisition/PO approval hierarchy?  ·  Blanket/contract agreements?  ·  Catalogs & punchout?  ·  Procurement contracts?

Validate: Req-to-PO-to-receipt tested; agreements loaded

Load: Procurement config; PO/Agreement FBDI.

### Core HR (workers & assignments)  ·  HCM · Phase 3

Person, employment, assignment model. Source of truth for workers used downstream by Payroll, Comp, Expenses, ICM.

Prerequisites: Workforce structures (Legal Employer, Depts, Jobs, Grades), Security: roles, data roles, users

Discovery: Worker population & countries?  ·  Employment model (2-tier single/multiple)?  ·  Actions & reasons?  ·  Conversion source for workers?

Validate: Active worker assignments loaded and reconciled to source

Load: HCM Data Loader (HDL) worker.dat; Spreadsheet Loader for low volume.

### CX Sales: Resources & Sales hierarchy  ·  CX (Sales/Service/CPQ) · Phase 3

Internal resources, resource org, and the sales hierarchy. Drives ownership, forecasting, and ICM participants.

Prerequisites: Security: roles, data roles, users, Customer master (Accounts & Sites)

Discovery: Sales org structure & hierarchy?  ·  Resources from HCM or standalone?  ·  Roles (sales rep, manager, channel)?

Validate: Resource org + hierarchy built; resources active

Load: Manage Resources; HCM sync or Resource import.

### CX Sales: Products & Catalog  ·  CX (Sales/Service/CPQ) · Phase 3

Sales product groups/catalog used by opportunities, CPQ, and quotes. Tied to item master.

Prerequisites: Inventory orgs & Item Master (PIM)

Discovery: Sales catalog structure?  ·  Product groups vs items?  ·  Recommendations/eligibility?

Validate: Sales catalog published and usable on opportunities

Load: Product Group setup; sync from PIM.

### Expenses  ·  ERP / Financials · Phase 4

Employee expense reports flowing to AP. Needs workers (HCM) + AP.

Prerequisites: Payables (AP), Core HR (workers & assignments)

Discovery: Expense types & policies?  ·  Card integration?  ·  Approval rules?

Validate: Expense submission → AP invoice tested end to end

Load: Expenses setup; corporate card feed.

### Order Management + Global Order Promising  ·  SCM / Procurement / Mfg · Phase 4

Sales order capture, orchestration, fulfillment, billing to AR. Heavy cross-pillar dependency.

Prerequisites: Inventory orgs & Item Master (PIM), Pricing, Customer master (Accounts & Sites), Receivables (AR)

Discovery: Order sources (CX, EDI, manual)?  ·  Orchestration processes?  ·  ATP/GOP sourcing rules?  ·  Billing to AR via AutoInvoice?

Validate: Order-to-cash flow tested across OM → fulfillment → AR

Load: OM/GOP config; Order Import; pricing & customer master prerequisites.

### Cost Management  ·  SCM / Procurement / Mfg · Phase 4

Inventory valuation, cost accounting, COGS to GL. Depends on Inventory + GL.

Prerequisites: Inventory orgs & Item Master (PIM), General Ledger

Discovery: Cost org & cost books?  ·  Costing method (std/avg/FIFO)?  ·  Receipt/COGS accounting?

Validate: Cost accounting runs clean; distributions post to GL

Load: Cost Mgmt config; standard cost FBDI.

### Manufacturing  ·  SCM / Procurement / Mfg · Phase 4

Work definitions, work orders, execution. Foundation for Maintenance & Quality on the production side.

Prerequisites: Inventory orgs & Item Master (PIM)

Discovery: Discrete/process?  ·  Work areas & resources?  ·  Work definitions source?

Validate: Work order execution tested

Load: Manufacturing config; work definition import.

### Absence Management  ·  HCM · Phase 4

Leave plans and accruals; prerequisite for Payroll absence integration.

Prerequisites: Core HR (workers & assignments)

Discovery: Absence plan types & accrual rules?  ·  Carryover/limits?

Validate: Plans configured and enrolled

Load: Absence Administration setup; HDL for enrollments.

### Payroll  ·  HCM · Phase 4

Elements, balances, payroll definitions, costing to GL. Heavy; depends on Core HR and ledger costing.

Prerequisites: Core HR (workers & assignments)

Discovery: In-scope payroll countries (legislations)?  ·  Elements & earnings/deductions?  ·  Costing to which COA segments?  ·  Bank/payment methods?

Validate: Payroll definitions, elements, costing, and a clean test run complete

Load: Payroll setup tasks; HDL for elements/balances; FBDI for batch entries.

### Compensation & Benefits  ·  HCM · Phase 4

Salary, comp plans, and benefits enrollment. Depends on grades and worker data.

Prerequisites: Core HR (workers & assignments)

Discovery: Comp cycles & plans?  ·  Benefits programs & eligibility?  ·  Total comp statement?

Validate: Plans and eligibility configured; test enrollments pass

Load: Compensation/Benefits setup; HDL where supported.

### CX Sales: Territories  ·  CX (Sales/Service/CPQ) · Phase 4

Territory dimensions and assignment. Drives account/opportunity ownership and ICM crediting.

Prerequisites: CX Sales: Resources & Sales hierarchy, Customer master (Accounts & Sites)

Discovery: Territory dimensions (geo, industry, product, named account)?  ·  Assignment rules?  ·  Forecast participation?

Validate: Territories proposed/activated; assignment runs correctly

Load: Enterprise Territory Mgmt; territory import.

### CX Sales: Leads, Opportunities, Forecasting  ·  CX (Sales/Service/CPQ) · Phase 4

The selling motion — leads, opportunities, pipeline, forecast. Depends on products, territories, resources.

Prerequisites: CX Sales: Products & Catalog, CX Sales: Territories

Discovery: Sales stages & methodology?  ·  Lead qualification & routing?  ·  Forecast cadence & adjustments?

Validate: Lead→Opty→Forecast flow tested with real users

Load: Sales config; opportunity/lead import.

### Fusion Service (Service Requests)  ·  CX (Sales/Service/CPQ) · Phase 4

Case/SR management, queues, assignment, SLAs, knowledge. Depends on customers and products.

Prerequisites: Customer master (Accounts & Sites), CX Sales: Products & Catalog

Discovery: Channels (email, chat, portal)?  ·  SR categories & queues?  ·  Assignment & SLA milestones?  ·  Knowledge base?  ·  Field service / RMA?

Validate: SR intake → routing → SLA → resolution tested

Load: Service config; queues/SLA/assignment rules; knowledge import.

### Maintenance  ·  Maintenance & Quality · Phase 5

Asset maintenance, work orders, preventive maintenance. Depends on inventory/assets and the work-order engine.

Prerequisites: Inventory orgs & Item Master (PIM), Manufacturing

Discovery: Maintainable asset population?  ·  Preventive maintenance programs?  ·  Spare parts from inventory?  ·  Work order costing?

Validate: Asset + PM program + work order execution tested

Load: Maintenance config; asset import; PM forecast.

### Quality (Inspection)  ·  Maintenance & Quality · Phase 5

Inspection plans and quality results across receiving, manufacturing, and maintenance.

Prerequisites: Inventory orgs & Item Master (PIM)

Discovery: Inspection points (receiving/in-process/maintenance)?  ·  Specifications & dispositions?  ·  Nonconformance handling?

Validate: Inspection plans execute and capture results at chosen points

Load: Quality Inspection config.

### CPQ (Configure, Price, Quote)  ·  CX (Sales/Service/CPQ) · Phase 5

Guided selling, configuration, pricing, quoting, approvals. Integrates CX Sales → CPQ → Order/Commerce.

Prerequisites: CX Sales: Leads, Opportunities, Forecasting, Pricing

Discovery: Configurable products & rules?  ·  Pricing waterfall & discount approvals?  ·  Quote-to-order integration target (OM/Commerce)?  ·  Document/proposal templates?

Validate: Quote → approval → order integration tested

Load: CPQ admin (Configuration/Commerce/Pricing); BML; integration to CX & OM.

### Subscription Management  ·  CX Subscriptions · Phase 5

Recurring/usage billing and subscription-to-cash. Depends on products, pricing, customers, and AR for invoicing/revenue.

Prerequisites: Customer master (Accounts & Sites), Pricing, Receivables (AR)

Discovery: Subscription products & charge models (recurring/usage/one-time)?  ·  Billing frequency & proration?  ·  Renewals & amendments?  ·  Revenue recognition (RMCS)?  ·  Usage source/rating?

Validate: Subscription → bill → AR invoice → revenue tested end to end

Load: Subscription config; product/price prerequisites; AR integration.

### Marketing & Eloqua  ·  CX Marketing & Eloqua · Phase 5

Campaigns, nurture, lead scoring with Eloqua, syncing leads/contacts to CX Sales. Quality of contact data is the gating factor.

Prerequisites: Customer Data Cleansing & TCA load, CX Sales: Leads, Opportunities, Forecasting

Discovery: Eloqua instance & integration (CX/B2B)?  ·  Lead scoring & nurture programs?  ·  Contact/lead sync direction & dedup?  ·  Consent/GDPR handling?

Validate: Contact sync + scoring + lead handoff to Sales tested

Load: Eloqua app setup; CX integration; contact sync.

### Partner Relationship Management  ·  PRM (Partners) · Phase 5

Partner accounts, programs, deal registration, partner portal. Extends CX Sales to the channel.

Prerequisites: CX Sales: Leads, Opportunities, Forecasting, Customer master (Accounts & Sites)

Discovery: Partner tiers & programs?  ·  Deal registration & approval?  ·  Partner portal & MDF?  ·  Partner users & data scope?

Validate: Partner onboarding + deal reg + portal tested

Load: PRM config; partner account import.

### ICM: Participants & roles  ·  ICM (Incentive Comp) · Phase 5

Comp participants mapped from HCM/Sales resources, with roles and pay groups. The 'who gets paid'.

Prerequisites: CX Sales: Resources & Sales hierarchy, Workforce structures (Legal Employer, Depts, Jobs, Grades)

Discovery: Participant source (HCM workers / sales resources)?  ·  Roles & pay groups?  ·  Manager rollup for rollup credit?

Validate: Participants loaded with roles, pay groups, and hierarchy

Load: Participant Mgmt; sync from HCM/Resources; participant import.

### ICM: Plans, Quota & Crediting  ·  ICM (Incentive Comp) · Phase 6

Compensation plans, measures, rate tables, quotas, and crediting rules (direct + rollup) tied to territories.

Prerequisites: ICM: Participants & roles, CX Sales: Territories

Discovery: Plan components & measures?  ·  Rate tables / accelerators?  ·  Quota source & allocation?  ·  Crediting rules (territory, named account, rollup)?

Validate: Plans assigned, quotas loaded, crediting validated on sample

Load: Plan design; rate tables; quota import; crediting rules.

### ICM: Transactions, Calculation & Payment  ·  ICM (Incentive Comp) · Phase 6

Feed orders/invoices as comp transactions, run calculation, dispute, approve, and pay (to Payroll/AP). The cross-pillar payoff.

Prerequisites: ICM: Plans, Quota & Crediting, Order Management + Global Order Promising, Receivables (AR)

Discovery: Transaction source (OM orders, AR invoices, custom)?  ·  Calc frequency & true-ups?  ·  Dispute workflow?  ·  Payment to Payroll/AP?

Validate: Import → calculate → approve → pay tested with reconciled amounts

Load: Transaction import; Calculation; Payment batch to Payroll/AP.

# Appendix B — Detect & validate SQL (run as BIP data model)

Geographies (TCA)

SELECT 'Geographies' obj, COUNT(*) cnt FROM hz_geographies

Readiness: Geographies exist for every country used by LE/BU/customers

Enterprise definition

SELECT 'Enterprise' obj, COUNT(*) cnt FROM hr_organization_units hou WHERE hou.organization_type='ENTERPRISE'

Readiness: Exactly one enterprise defined

Currencies & conversion rates

SELECT 'Enabled Currencies' obj, COUNT(*) cnt FROM fnd_currencies WHERE enabled_flag='Y'

Readiness: Ledger currency + all transaction currencies enabled; rate types defined

Chart of Accounts (segments & value sets)

SELECT 'COA Structures' obj, COUNT(*) cnt FROM gl_code_combinations WHERE rownum<2 UNION ALL SELECT 'Value Sets', COUNT(*) FROM fnd_vs_value_sets

Readiness: COA structure + instance defined, all segments mapped to value sets, qualifiers set

Accounting calendar

SELECT 'Calendars' obj, COUNT(DISTINCT period_set_name) cnt FROM gl_periods

Readiness: Calendar covers conversion history + current + future periods

Primary Ledger (+ SLA method)

SELECT 'Ledgers' obj, COUNT(*) cnt FROM gl_ledgers WHERE ledger_category_code='PRIMARY'

Readiness: Primary ledger complete and assigned; periods opened

Legal Entities & jurisdictions

SELECT 'Legal Entities' obj, COUNT(*) cnt FROM xle_entity_profiles

Readiness: Every LE has a registration and is assigned to a ledger

Business Units & functions

SELECT 'Business Units' obj, COUNT(*) cnt FROM fun_all_business_units_v

Readiness: Each BU has ledger + default LE + required business functions assigned

Reference Data Sets (SetID)

SELECT 'Reference Sets' obj, COUNT(*) cnt FROM fnd_setid_sets

Readiness: Set determinants assigned for each BU and set-enabled object

Locations

SELECT 'Locations' obj, COUNT(*) cnt FROM per_locations_legislative_g

Readiness: All operating sites defined with valid geography

Security: roles, data roles, users

SELECT 'Active Users' obj, COUNT(*) cnt FROM per_users WHERE active_flag='Y'

Readiness: Admin + functional impl users provisioned with correct roles and data scope

Customer Data Cleansing & TCA load

SELECT 'Parties' o,COUNT(*) c FROM hz_parties UNION ALL SELECT 'Cust Accounts',COUNT(*) FROM hz_cust_accounts

Readiness: Golden party set deduped, standardized, hierarchy built, ready to load

Customer master (Accounts & Sites)

SELECT 'Customer Sites' obj, COUNT(*) cnt FROM hz_cust_acct_sites_all

Readiness: Accounts + sites + uses loaded; reconciled to golden set; no dupes

General Ledger

SELECT 'GL Journals' obj, COUNT(*) cnt FROM gl_je_headers WHERE rownum<2

Readiness: Period open, journal import working, opening balances loaded & reconciled

Tax

SELECT 'Tax Regimes' obj, COUNT(*) cnt FROM zx_regimes_b

Readiness: Regimes/rates/rules tested on sample AP & AR transactions

Supplier model

SELECT 'Suppliers' obj, COUNT(*) cnt FROM poz_suppliers

Readiness: Suppliers + sites + bank accounts loaded & deduped

Inventory orgs & Item Master (PIM)

SELECT 'Inv Orgs' o,COUNT(*) c FROM inv_org_parameters UNION ALL SELECT 'Items',COUNT(*) FROM egp_system_items_b

Readiness: Inventory orgs created; item master loaded with required attributes

Workforce structures (Legal Employer, Depts, Jobs, Grades)

SELECT 'Departments' o,COUNT(*) c FROM per_departments UNION ALL SELECT 'Jobs',COUNT(*) FROM per_jobs_f UNION ALL SELECT 'Grades',COUNT(*) FROM per_grades_f

Readiness: Legal employer(s), department tree, jobs/positions, grades all defined

Cash Management & Banks

SELECT 'Bank Accounts' obj, COUNT(*) cnt FROM ce_bank_accounts

Readiness: Bank accounts set up, statement import & reconciliation tested

Payables (AP)

SELECT 'AP Invoices' obj, COUNT(*) cnt FROM ap_invoices_all WHERE rownum<2

Readiness: Payment process tested; open invoices loaded & reconciled

Receivables (AR)

SELECT 'AR Transactions' obj, COUNT(*) cnt FROM ra_customer_trx_all WHERE rownum<2

Readiness: AutoInvoice + receipts tested; open AR loaded & reconciled

Fixed Assets (FA)

SELECT 'FA Books' obj, COUNT(*) cnt FROM fa_book_controls

Readiness: Books & categories defined; asset conversion loaded; depreciation tested

Pricing

SELECT 'Price Lists' obj, COUNT(*) cnt FROM qp_pricing_pte_v WHERE rownum<2

Readiness: Price lists loaded; pricing returns correct results on test orders

Purchasing & Self-Service Procurement

SELECT 'Purchase Orders' obj, COUNT(*) cnt FROM po_headers_all WHERE rownum<2

Readiness: Req-to-PO-to-receipt tested; agreements loaded

Core HR (workers & assignments)

SELECT 'Workers' obj, COUNT(*) cnt FROM per_all_people_f

Readiness: Active worker assignments loaded and reconciled to source

CX Sales: Resources & Sales hierarchy

SELECT 'Sales Resources' obj, COUNT(*) cnt FROM zmm_resources_v WHERE rownum<2

Readiness: Resource org + hierarchy built; resources active

CX Sales: Products & Catalog

SELECT 'Sales Products' obj, COUNT(*) cnt FROM qsc_products_v WHERE rownum<2

Readiness: Sales catalog published and usable on opportunities

Expenses

SELECT 'Expense Reports' obj, COUNT(*) cnt FROM exm_expense_reports WHERE rownum<2

Readiness: Expense submission → AP invoice tested end to end

Order Management + Global Order Promising

SELECT 'Sales Orders' obj, COUNT(*) cnt FROM doo_headers_all WHERE rownum<2

Readiness: Order-to-cash flow tested across OM → fulfillment → AR

Cost Management

SELECT 'Cost Orgs' obj, COUNT(*) cnt FROM cst_cost_org_books WHERE rownum<2

Readiness: Cost accounting runs clean; distributions post to GL

Manufacturing

SELECT 'Work Orders' obj, COUNT(*) cnt FROM wie_work_orders_b WHERE rownum<2

Readiness: Work order execution tested

Absence Management

SELECT 'Absence Plans' obj, COUNT(*) cnt FROM anc_absence_plans_f

Readiness: Plans configured and enrolled

Payroll

SELECT 'Payroll Defns' obj, COUNT(*) cnt FROM pay_all_payrolls_f

Readiness: Payroll definitions, elements, costing, and a clean test run complete

Compensation & Benefits

SELECT 'Comp Plans' obj, COUNT(*) cnt FROM cmp_salary_bases

Readiness: Plans and eligibility configured; test enrollments pass

CX Sales: Territories

SELECT 'Territories' obj, COUNT(*) cnt FROM moo_terr_all_v WHERE rownum<2

Readiness: Territories proposed/activated; assignment runs correctly

CX Sales: Leads, Opportunities, Forecasting

SELECT 'Opportunities' obj, COUNT(*) cnt FROM moo_opty_all_b WHERE rownum<2

Readiness: Lead→Opty→Forecast flow tested with real users

Fusion Service (Service Requests)

SELECT 'Service Requests' obj, COUNT(*) cnt FROM svc_service_requests WHERE rownum<2

Readiness: SR intake → routing → SLA → resolution tested

Maintenance

SELECT 'Maint Work Orders' obj, COUNT(*) cnt FROM mnt_work_orders_b WHERE rownum<2

Readiness: Asset + PM program + work order execution tested

Quality (Inspection)

SELECT 'Inspection Plans' obj, COUNT(*) cnt FROM qa_plans WHERE rownum<2

Readiness: Inspection plans execute and capture results at chosen points

CPQ (Configure, Price, Quote)

SELECT 'CPQ Quotes' obj, COUNT(*) cnt FROM /* CPQ is separate stack */ dual

Readiness: Quote → approval → order integration tested

Subscription Management

SELECT 'Subscriptions' obj, COUNT(*) cnt FROM oss_subscriptions WHERE rownum<2

Readiness: Subscription → bill → AR invoice → revenue tested end to end

Marketing & Eloqua

SELECT 'Marketing Leads' obj, COUNT(*) cnt FROM mkt_leads WHERE rownum<2

Readiness: Contact sync + scoring + lead handoff to Sales tested

Partner Relationship Management

SELECT 'Partner Accounts' obj, COUNT(*) cnt FROM zpm_partners_v WHERE rownum<2

Readiness: Partner onboarding + deal reg + portal tested

ICM: Participants & roles

SELECT 'ICM Participants' obj, COUNT(*) cnt FROM cn_srp_periods_all WHERE rownum<2

Readiness: Participants loaded with roles, pay groups, and hierarchy

ICM: Plans, Quota & Crediting

SELECT 'Comp Plans' obj, COUNT(*) cnt FROM cn_comp_plans_all_b WHERE rownum<2

Readiness: Plans assigned, quotas loaded, crediting validated on sample

ICM: Transactions, Calculation & Payment

SELECT 'Comp Transactions' obj, COUNT(*) cnt FROM cn_tp_transactions_all WHERE rownum<2

Readiness: Import → calculate → approve → pay tested with reconciled amounts